## PRODUCT BACKLOG
PRODUCT BACKLOG
REQUIREMENT | DESCRIPTION | USER STORIES | USER ACCEPTANCE TEST | SPRINT #
User Verification | A 3rd party identity provider should be used. 3 roles: Resident, Facility Staff, Admin
|  | As a system administrator, I want to securely log into my account so that I can manage users and oversee facility operations | Given that I am a system administrator , when I login securely, then I can manage manage users and the facility operations. | 1
|  | As a resident, I want to register a new account, so that I can access and use the features of the website. | Given that I am a resident with a google a/c, when I register then I can access features of this site | 1
|  | As a resident, I want to log into my account, so that I can make bookings, report issues and receive notifications | Given that I am a resident and I have registered an account, when I sign in I am taken to my dashboard and I can make bookings, report any issues and receive notifications. | 1
|  | As a staff member, I want to register a new account, so that I can access and use the features of the website | Given that I am a staff member with a google a/c, when I register then I can access and use features of this site. | 1
|  | As a staff member, I want to log into my account, so that I can manage facility-related tasks assigned to my role | Given that I am a staff member, when I login into my account, then I can access the tasks assigned to my role and manage them. | 1
User Management | Admins should be able to manage users – onboard members, revoke access, assign roles, etc.
|  | As a system administrator, I want to onboard users, so they have full access to the relevant website features | Given that I am a system administrator, when I onboard a user, then they have full access to the relevant website features. | 2
|  | As a system administrator, I want to assign roles such as resident or staff to users, so that they have access to the appropriate features and permissions within the platform | Given that I am logged in as a systems administrator and I am on the user management page, when I select a user from the list , then I can assign a role to the user. | 2
|  | As a system administrator, I want to remove staff members from the website, so that they no longer have access to the website’s features | Given that I am a system administrator, when I remove a staff member, then they are blocked from using the website’s features. | 2
|  | As a system administrator, I want to remove residents from the website, so that they no longer have access to the website’s features | Given that I am a system administrator, when I remove a resident, then they are blocked from using the website’s features. | 2
Booking System | Residents should be able to reserve sports facilities for specific time slots. Admins can approve/block bookings as needed
|  | As a resident, I want to book a facility so that I can have exclusive access to it | Given that I am a resident and the facility is available for booking, when I make a booking , then I am allocated to the facility. | 2
|  | As a resident, I want to cancel a booking as I no longer need it | Given that I am a resident and I have already booked a facility, when I cancel my booking, then the facility becomes available for new booking. | 2
|  | As a system administrator, I want to block bookings, so that the facility becomes available | Given that I am a system administrator and that a resident has booked a facility, when I block the booking, then the facility that was booked becomes available for new bookings. | 2
|  | As a system administrator, I want to approve bookings, so that residents have access to the facility | Given that I am a system administrator, when a resident makes a booking, then I can approve the booking so that the resident can access to the facility. | 2
Maintenance Reporting | Users should be able to report facility issues. Facility staff should update status and provide feedback.
|  | As a resident, I want to report issues with facilities so that staff can tend to them. | Given that I have been approved as a resident , when I report issues with a facility, then the staff is notified and can then tend to the issues. | 3
|  | As a system administrator, I want to assign reports to staff members so that they can tend to them. | Given that I am a system administrator, when I assign reports to staff members, then the respective staff member can tend to the issue assigned to them. | 3
|  | As a staff member, I want to be notified when issues are assigned to me, so that I can tend to them. | Given that I am staff member, when issues are assigned to me , then I am notified and can tend to the issue. | 3
|  | As a staff member, I want to update the status of a facility so that the system administrator can track progress. | Given that I am a staff member, when I update the status of a facility, then the system administrator can track the maintenance progress of that facility. | 3
Events & Notifications | Admins should be able to create events (e.g., tournaments). Users should receive notifications about upcoming events and maintenance closures
|  | As a system administrator, I want to create events so that residents can be notified. | Given that I am a system administrator, when I create events, then the residents are notified about upcoming events. | 3
|  | As a resident, I want to receive notifications about upcoming events, so that I can participate. | Given that I am a resident, when an event is created, then I receive a notification and I can then participate in the event. | 3
|  | As a resident, I want to receive notifications about maintenance closures, so that I can plan accordingly. | Given that I am a resident, when a facility is under maintenance, then I receive a notification and I can plan accordingly. | 3
Reporting | At least 3 dashboard reports: Usage trends by facility, maintenance reports (open vs closed), custom view. Reports should be exportable as CSV or PDFs
|  | As a system administrator, I want to track the performance of maintenance staff so that I can manage them. | Given that I am a system administrator, when I go to the maintenance page then I can track the performance of maintenance staff and manage them. | 4
|  | As a system administrator, I want to generate key reports with flexible filters to analyse them over different periods. | Given that I am a system administrator, when I access the dashboard and select the generate report option then I can generate key reports with flexible filters to analyse them over different periods. | 4
|  | As a system administrator, I want to export dashboard reports as PDFs so that I can store, share, and print them. | Given that I am a system administrator, when I access the reports dashboard then I can export the reports as PDF to store, share and print them. | 4
|  | As a system administrator, I want to access a dashboard to see usage trends, maintenance reports, and a custom view. | Given that I am a system administrator, when I access the dashboard then I can see usage trends, maintenance reports and a custom view. | 4
Weather | Notify users of weather conditions affecting outdoor facilities.
|  | As a system administrator, I want to see the weather when I create an event, so that I can plan accordingly | Given that I am a system administrator, when I access my home page, then I will be informed of the current weather | 4
|  | As a s resident I want to see the weather when I make a booking, so that I can plan accordingly | Given that I am a resident, when I make access my home page, then I will be informed of the current weather | 4

## Sprint1
SPRINT 1
USER STORY | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a system administrator, I want to securely log into my account so that I can manage users and oversee facility operations | 25
Set up Google OAuth credentials |  | Dylan Naidoo | Complete | 1 | 1 | 0 |  |  |  | 0
Set up FireStore Database |  | Dylan Naidoo | Complete | 1 | 1 | 0 |  |  |  | 0
Create user table in DB |  | Dylan Naidoo | Complete | 1 | 1 | 0 |  |  |  | 0
Insert System Administrator into DB |  | Dylan Naidoo | Complete | 1 | 1 | 0 |  |  |  | 0
Create HTML structure for landing page |  | Karabelo Borotho | Complete | 2 | 1 | 0 |  |  |  | 0
Style landing page |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 1 | 0 |  |  |  | 0
Implement frontend "Sign in with Google" button |  | Jayden Harold | Complete | 2 | 1 | 1 | 0 |  |  | 0
Backend: Verify Google ID token and create session |  | Tariro Muvevi | Complete | 3 | 3 | 2 | 1 | 0 |  | 0
Check role and redirect to admin dashboard |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 3 | 0 | 0
Restrict access to admin routes |  | Jayden Harold, Karabo Bopape | Complete | 2 | 2 | 2 | 2 | 2 | 0 | 0
Error handling for admin login |  | Karabo Bopape | Complete | 2 | 2 | 1 | 1 | 1 | 0 | 0
Testing: Create mock admin and sign in |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 0
As a resident, I want to register a new account, so that I can access and use the features of the website. | 20
Set up Google OAuth credentials |  | Dylan Naidoo | Complete
Set up FireStore Database |  | Dylan Naidoo | Complete
Create user table in DB |  | Dylan Naidoo | Complete
Create HTML structure for landing page |  | Karabelo Borotho | Complete
Style landing page |  | Karabelo Borotho, Jayden Harold | Complete
Implement frontend "Sign up with Google" button |  | Jayden Harold | Complete | 2 | 1 | 1 | 0 |  |  | 0
Backend: Verify Google ID token and create session |  | Tariro Muvevi | Complete
Redirect to sign in if account exists |  | Karabo Bopape | Complete | 2 | 2 | 2 | 1 | 0
Store user info in DB with default "pending" status and "resident" role |  | Dylan Naidoo, Tariro Muvevi | Complete | 5 | 5 | 3 | 1 | 0
Check role and redirect to resident dashboard |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 3 | 0 | 0
Fetch and display name and status in dashbaord |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 3 | 0 | 0
Testing: Create mock resident and sign up |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 0
As a resident, I want to log into my account, so that I can make bookings, report issues and receive notifications | 7
Implement frontend "Sign in with Google" button |  | Jayden Harold | Complete
Backend: Verify Google ID token and create session |  | Tariro Muvevi | Complete
Check role and redirect to resident dashboard |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Redirect to sign up if account does not exist |  | Karabo Bopape | Complete | 2 | 2 | 2 | 1 | 0 |  | 0
Fetch and display name and status in dashbaord |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Testing: Create mock resident and sign in |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 0
As a staff member, I want to register a new account, so that I can access and use the features of the website | 13
Set up Google OAuth credentials |  | Dylan Naidoo | Complete
Set up FireStore Database |  | Dylan Naidoo | Complete
Create user table in DB |  | Dylan Naidoo | Complete
Create HTML structure for landing page |  | Karabelo Borotho | Complete
Style landing page |  | Karabelo Borotho, Jayden Harold | Complete
Implement frontend "Sign up with Google" button |  | Jayden Harold | Complete
Backend: Verify Google ID token and create session |  | Tariro Muvevi | Complete
Redirect to sign in if account exists |  | Karabo Bopape | Complete
Store user info in DB with default "pending" status and "staff" role |  | Dylan Naidoo, Tariro Muvevi | Complete | 5 | 5 | 3 | 1 | 0 |  | 0
Check role and redirect to staff dashboard |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 3 | 0 | 0
Fetch and display name and status in dashbaord |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Testing: Create mock staff member and sign up |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 0
As a staff member, I want to log into my account, so that I can manage facility-related tasks assigned to my role | 5
Implement frontend "Sign in with Google" button |  | Jayden Harold | Complete
Backend: Verify Google ID token and create session |  | Tariro Muvevi | Complete
Check role and redirect to staff dashboard |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Redirect to sign up if account does not exist |  | Karabo Bopape | Complete
Fetch and display name and status in dashbaord |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Testing: Create mock staff member and sign in |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 0
TOTAL |  |  |  | 70 | 66 | 54 | 45 | 40 | 25 | 0

## Sprint2
SPRINT 2
USER STORY | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a system administrator, I want to onboard users, so they have full access to the relevant website features | 25
Approve button - set status to "approved" |  | Jayden Harold, Dylan Naidoo, Tariro Muvevi | Complete | 5 | 3 | 0 |  |  |  | 0
Add resident and staff tabs to admin page |  | Karabelo Borotho | Complete | 2 | 2 | 0 |  |  |  | 0
Fetch and display all pending residents in resident page |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 2 | 0 |  |  |  | 0
Fetch and display all pending staff in staff page |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 2 | 0 |  |  |  | 0
Testing: Create mock resident and approve |  | Karabo Bopape | Complete | 5 | 5 | 4 | 3 | 2 | 1 | 0
Testing: Create mock staff member and approve |  | Karabo Bopape | Complete | 5 | 5 | 4 | 3 | 2 | 1 | 0
As a system administrator, I want to assign roles such as resident or staff to users, so that they have access to the appropriate features and permissions within the platform | 0
Approve button - set status to "approved" |  | Jayden Harold, Dylan Naidoo, Tariro Muvevi | Complete
Add resident and staff tabs to admin page |  | Karabelo Borotho | Complete
Fetch and display all pending residents in resident page |  | Tariro Muvevi, Jayden Harold | Complete
Fetch and display all pending staff members in staff page |  | Tariro Muvevi, Jayden Harold | Complete
As a system administrator, I want to remove staff members from the website, so that they no longer have access to the website’s features | 15
Remove button |  | Jayden Harold | Complete | 2 | 2 | 0 |  |  |  | 0
Delete staff member from DB |  | Tariro Muvevi | Complete | 3 | 3 | 1 | 0 |  |  | 0
Alert message to confirm action |  | Karabo Bopape | Complete | 1 | 1 | 1 | 0 |  |  | 0
Fetch and display approved staff members in staff page |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 2 | 0 |  |  |  | 0
Testing: Create mock staff member and remove |  | Karabo Bopape | Complete | 5 | 5 | 4 | 3 | 2 | 1 | 0
As a system administrator, I want to remove residents from the website, so that they no longer have access to the website’s features | 15
Remove button |  | Jayden Harold | Complete | 2 | 2 | 0 |  |  |  | 0
Delete resident from DB |  | Tariro Muvevi | Complete | 3 | 3 | 1 | 0 |  |  | 0
Alert message to confirm action |  | Karabo Bopape | Complete | 1 | 1 | 1 | 0 |  |  | 0
Fetch and display approved residents in residents page |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 4 | 2 | 0 |  |  |  | 0
Testing: Create mock staff member and remove |  | Karabo Bopape | Complete | 5 | 5 | 4 | 3 | 2 | 1 | 0
As a resident, I want to book a facility so that I can have exclusive access to it | 35
Create individual facility pages for residents to browse |  | Karabelo Borotho, Jayden Harold | Complete | 3 | 3 | 3 | 0 |  |  | 0
Creeate facility table in DB and set defult status to "available" |  | Dylan Naidoo | Complete | 2 | 2 | 2 | 0 |  |  | 0
Create 'book a facility' page |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 0 |  |  | 0
Creating bookings page |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 0 |  |  | 0
Populate facilities selector based on sport selected |  | Tariro Muvevi | Complete | 2 | 2 | 2 | 1 | 0 |  | 0
Bookings popup with information before confirming booking |  | Karabo Bopape | Complete | 2 | 2 | 2 | 1 | 0 |  | 0
Prevent residents from making bookings if the facility is under maintenance |  | Karabo Bopape | Complete | 3 | 3 | 3 | 2 | 1 | 0 | 0
Create booking in DB and set default status to "pending" |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 4 | 4 | 3 | 2 | 0 | 0
Fetch and display bookings in bookings page for bookings made by that particular resident |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete | 4 | 4 | 4 | 4 | 3 | 0 | 0
Ensure residents cannot book past dates |  | Jayden Harold | Complete | 1 | 1 | 1 | 1 | 1 | 0 | 0
Testing bookings redirect |  | Karabo Bopape | Complete | 5 | 5 | 5 | 4 | 2 | 1 | 0
Testing: Create mock booking, ensure no conflicts and correct storage |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 4 | 3 | 0
As a resident, I want to cancel a booking as I no longer need it | 11
Fetch and display bookings in bookings page for bookings made by that particular resident |  | Dylan Naidoo, Jayden Harold, Tariro Muvevi | Complete
Cancel button |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 1 | 0 | 0
Delete staff member from DB |  | Tariro Muvevi, Dylan Naidoo | Complete | 3 | 3 | 3 | 3 | 2 | 0 | 0
Alert message to confirm action |  | Karabo Bopape | Complete | 1 | 1 | 1 | 1 | 1 | 0 | 0
Testing: Create mock booking and cancel |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 4 | 2 | 0
As a system administrator, I want to approve bookings, so that residents have access to the facility | 9
Create bookings page for admin |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 0 |  |  | 0
Fetch and display all pending bookings |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 4 | 4 | 4 | 3 | 0 | 0
Approve button - set status to "approved" |  | Jayden Harold, Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 2 | 0 | 0
As a system administrator, I want to block bookings, so that the facility becomes available | 15
Fetch and display all approved bookings |  | Tariro Muvevi, Jayden Harold | Complete | 4 | 4 | 4 | 4 | 3 | 0 | 0
Fetch and displau all pending bookings |  | Tariro Muvevi, Jayden Harold | Complete
Cancel/block button |  | Jayden Harold, Tariro Muvevi | Complete | 2 | 2 | 2 | 2 | 1 | 0 | 0
Alert message to confirm action |  | Karabo Bopape | Complete | 1 | 1 | 1 | 1 | 1 | 0 | 0
Delete booking from DB |  | Dylan Naidoo | Complete | 3 | 3 | 3 | 3 | 2 | 0 | 0
Notify resident that their booking has been blocked/cancelled |  | Dylan Naidoo, Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 4 | 3 | 0
TOTAL |  |  |  | 125 | 115 | 90 | 66 | 45 | 13 | 0

## Sprint3
SPRINT 3
USER STORY | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
As a resident, I want to report issues with facilities so that staff can tend to them. | 18
Create maintenance page for residents to report issues |  | Karabelo Borotho, Jayden Harold | Complete | 2 | DAY 1: 2; DAY 2: 0 | 0
Populate facilities selector from facilities table in DB |  | Tariro Muvevi | Complete | 3 | DAY 1: 2; DAY 2: 1; DAY 3: 0 | 0
Create maintenance table in DB |  | Dylan Naidoo | Complete | 3 | DAY 1: 3; DAY 2: 2; DAY 3: 0 | 0
Set status attribute of facility to 'under maintenance' in facilities table |  | Dylan Naidoo | Complete | 3 | DAY 1: 3; DAY 2: 2; DAY 3: 0 | 0
Process view for resident reporting maintenance issue |  | Karabelo Borotho | Complete | 3 | DAY 1: 3; DAY 2: 2; DAY 3: 0 | 0
Create maintenance report in DB with default status as "reported" and assigned to as "TBD" |  | Tariro Muvevi, Jayden Harold, Dylan Naidoo | Complete | 4 | DAY 1: 3; DAY 2: 2; DAY 3: 1; DAY 4: 0 | 0
As a system administrator, I want to assign reports to staff members so that they can tend to them. | 15
Create maintenance page for admins to see maintenance reports |  | Karabelo Borotho, Jayden Harold | Complete | 2 | DAY 1: 2; DAY 2: 0 | 0
Fetch and display all reported maintenance issues |  | Jayden Harold, Tariro Muvevi | Complete | 4 | DAY 1: 4; DAY 2: 4; DAY 3: 3; DAY 4: 0 | 0
Populate assigned to selector based on all users with role staff |  | Jayden Harold | Complete | 3 | DAY 1: 3; DAY 2: 3; DAY 3: 2; DAY 4: 1; DAY 5: 0 | 0
Set status attribute to "assigned" when a staff member is selected |  | Tariro Muvevi, Jayden Harold | Complete | 3 | DAY 1: 3; DAY 2: 3; DAY 3: 2; DAY 4: 1; DAY 5: 0 | 0
Set "assigned to" attribute in DB to the selected staff member |  | Tariro Muvevi, Jayden Harold | Complete | 3 | DAY 1: 3; DAY 2: 3; DAY 3: 2; DAY 4: 1; DAY 5: 0 | 0
As a staff member, I want to be notified when issues are assigned to me, so that I can tend to them. | 4
Create maintenance page for staff members |  | Karabelo Borotho, Jayden Harold | Complete | 1 | DAY 1: 1; DAY 2: 0 | 0
Fetch and display all maintenance issues assigned to that staff member |  | Tariro Muvevi | Complete | 3 | DAY 1: 3; DAY 2: 3; DAY 3: 3; DAY 4: 2; DAY 5: 0 | 0
As a staff member, I want to update the status of a facility so that the system administrator can track progress. | 6
Update status attribute based on progress selected |  | Tariro Muvevi | Complete | 3 | DAY 1: 3; DAY 2: 3; DAY 3: 3; DAY 4: 2; DAY 5: 0 | 0
Set facility status back to 'available' when maintenance issue is closed |  | Dylan Naidoo | Complete | 2 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 0 | 0
Update admin maintenance page |  | Jayden Harold, Tariro Muvevi | Complete | 1 | DAY 1: 1; DAY 2: 1; DAY 3: 0 | 0
As a system administrator, I want to create events so that residents can be notified. | 32
Create events page for admins |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  |  |  | 0
Ensure admin cannot create events for past dates |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  |  |  | 0
Create events table in DB |  | Dylan Naidoo | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 |  |  |  | 0
Populate facilities selector based on sport selected |  | Tariro Muvevi | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  |  |  | 0
Check that the facility is not under maintenance and that there are no conflicting events |  | Karabo Bopape | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 |  |  |  | 0
Create event in events table |  | Dylan Naidoo | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 |  |  |  | 0
Fetch and display events in events page |  | Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 |  |  |  | 0
Update bookings page to check that there are no events on the day the resident wishes to make a booking |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 2 | 1 | 0 | 0
Process view for admin creating an event |  | Karabelo Borotho | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
Testing: Create mock event, ensure no conflicts and correct storage |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0
Update landing page to display closest approaching event |  | Dylan Naidoo | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0
As a resident, I want to receive notifications about upcoming events, so that I can participate. | 15
Create notifications table in DB |  | Dylan Naidoo | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Create notifications pages for residents |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Update events functionality to add a notification to the notification table |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
Set user attribute of events notifications to "all" so that the notification displays for all residents |  | Dylan Naidoo, Karabo Bopape | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Fetch and display events notifications in notifications page |  | Karabo Bopape, Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
As a resident, I want to receive notifications about maintenance closures, so that I can plan accordingly. | 10
Create notifications table in DB |  | Dylan Naidoo | Complete
Create notifications pages for residents |  | Karabelo Borotho, Jayden Harold | Complete
Update maintenance functionality to add a notification to the notification table |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
Set user attribute of maintenance notifications to "all" so that the notification displays for all residents |  | Dylan Naidoo, Karabo Bopape | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Fetch and display maintenance notifications in notifications page |  | Karabo Bopape, Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
TOTAL |  |  |  | 100 | 98 | 88 | 75 | 66 | 57 | 44 | 34 | 33 | 25 | 10 | 0

## Sprint4
SPRINT 4
USER STORY | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
As a system administrator, I want to track the performance of maintenance staff so that I can manage them. | 30
Update maintenance table to include resolved date, and resolution time |  | Dylan Naidoo | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 1 | 0
Create a staff table to track staff performance |  | Dylan Naidoo | Complete | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 1 | 0
Update maintenance functionality to add resolved date to maitenance reports |  | Tariro Muvevi, Dylan Naidoo | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 0
Update admin maintenance page to show staff performance |  | Tariro Muvevi | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0
Calculate resolution time based on reported date and resolved date |  | Tariro Muvevi | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 0
Calculate average resolution time for each staff member based on number of issues resolved and resolution time |  | Tariro Muvevi | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 0
Keep track of number of issued resolved and current workload for each staff member |  | Tariro Muvevi | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 0
As a system administrator, I want to generate key reports with flexible filters to analyse them over different periods. | 40
Create script link to ChartJS |  | Karabelo Borotho, Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Create usage trends tab in dashboard |  | Karabelo Borotho, Karabo Bopape | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Create custom view tab in dashboard |  | Karabo Bopape | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Create graph section in maintenance page |  | Karabelo Borotho, Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Pie chart for maintenance issues showing open, closed, in progress |  | Jayden Harold, Dylan Naidoo | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
Bar Chart showing number of maintenance issues per facility |  | Jayden Harold, Dylan Naidoo | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
Display most popular facility |  | Karabelo Borotho, Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Bar Chart showing number of bookings per facility |  | Karabelo Borotho, Jayden Harold | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0
Testing: Create mock bookings and ensure correct graphing |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0
Testing: Create mock maintenance reports and ensure correct graphing |  | Karabo Bopape | Complete | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0
Add all graphs from maintenance and usage trends into custom view tab with flexible filters |  | Karabo Bopape | Complete | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0
As a system administrator, I want to export dashboard reports as PDFs so that I can store, share, and print them. | 8
Create script link to html2pdf |  | Jayden Harold | Complete | 1 | DAY 1: 1; DAY 2: 1; DAY 3: 1; DAY 4: 0 | 0
Create download PDF button |  | Jayden Harold | Complete | 1 | DAY 1: 1; DAY 2: 1; DAY 3: 1; DAY 4: 0 | 0
Add PDF Functionality to maintenance page |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  | 0
Add PDF Functionality to usage trends report |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  | 0
Add PDF Functionality to custom view report |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  |  | 0
As a system administrator, I want to access a dashboard to see usage trends, maintenance reports, and a custom view. | 2
Create admin dashboard |  | Karabelo Borotho | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
As a system administrator, I want to see the weather when I create an event, so that I can plan accordingly | 7
Create accont on OpenWeatherApi |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Link website to API |  | Jayden Harold | Complete | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
Fetch weather and display weather in admin home page |  | Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0
As a s resident I want to see the weather when I make a booking, so that I can plan accordingly | 3
Create accont on OpenWeatherApi |  | Jayden Harold | Complete
Link website to API |  | Jayden Harold | Complete
Fetch weather and display weather in resident home page |  | Jayden Harold | Complete | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0
TOTAL |  |  |  | 90 | 90 | 90 | 90 | 88 | 87 | 85 | 81 | 65 | 48 | 27 | 0